## Overview
			Retrospective 1			Retrospective 2				Retrospective 3			Retrospective 4

Kickoff	Sprint 1	Sprint 2	Sprint 3	Sprint 4	Sprint 5	Sprint 6		Sprint 7	Sprint 8	Sprint 9	Sprint 10	Sprint 11	Sprint 12	Sprint 13	Sprint 14	Sprint 15	Presentation / Sprint
	W08	W09	W10	W11	W12	W13	W14	W15	W16	W17	W18	W19	W20	W21	W22	W23	W24-W26

	project plan / completed				basic architecture / fixed			final technology / fixed		alpha release			beta release		feature / freeze	code / freeze	documentation / completed	Presentation
				basic requirements & / analysis completed				testing concept fixed									presentation / prepared
			task description / fixed														final release / / submission
		license & / usage rights defined

## Sprint Details
Sprint	Sprint 1	Sprint 2	Sprint 3	Sprint 4
Tag	0.1.0	0.2.0	0.3.0	0.4.0
Date	20.02.2018 – 27.02.2018	27.02.2018 - 06.03.2018	06.03.2018 – 13.03.2018	13.03.2018 – 20.03.2018
Milestones	- license & usage rights defined	- task description fixed	- basic requirements & analysis completed	- basic architecture fixed
Time Budget	40	40	40	40
Tasks	- setup remaining project infrastructure / - read ietf draft, XEP standards etc. / - compile list of open questions / - begin with chapter “initial situation” / - analyze existing python proof-of-concept	- collect non-functional requirements (NFRs) / - compile set of user stories / - draw wireframes / - research frameworks and technology: Prepare architectural decisions	- extend NFRs, user stories, wireframes / - make first architectural decisions / - further framework and technology research / - implement proof of concepts for ciritical components	- make big architectural decisions / - implement proof of concepts for ciritical components
Documents / / Chapters / / Artefacts		- chapter "Initial Situation" completed / - signed task description

Sprint	Sprint 5	Sprint 6	Sprint 7	Sprint 8
Tag	0.5.0	0.6.0	0.7.0	0.8.0
Date	20.03.2018 – 27.03.2018	27.03.2018 – 10.04.2018	10.04.2018 – 19.04.2018	19.04.2018 – 24.04.2018
Milestones		- final technology fixed / - testing concept fixed
Time Budget	40	80	40	40
Tasks	- implement proof of concepts for ciritical components / - draft testing concept	- implement proof of concepts for ciritical components / - finalise testing concept	- Implement most important user stories / - make further architectural decisions	- Implement most important user stories / - make further architectural decisions / - write integration tests
Documents / / Artefacts		- Chapter "Our Approach" completed

Sprint	Sprint 9	Sprint 10	Sprint 11	Sprint 12
Tag	0.9.0	0.10.0	0.11.0	0.12.0
Date	24.04.2018 – 01.05.2018	01.05.2018 – 08.05.2018	08.05.2018 – 15.05.2018	15.05.2018 – 22.05.2018
Milestones	- alpha release (29.04.2018)
Time Budget	40	40	40	40
Tasks	- Implement secondary user stories / - write integration tests	- Implement secondary user stories / - write integration tests	- Implement secondary user stories / - write integration tests	- Implement remainging user stories / - Improve code base / - write integration tests
Documents / / Artefacts	- alpha release bundle

Sprint	Sprint 13	Sprint 14	Sprint 15	Presentation Sprint
Tag	0.13.0	0.14.0	1.0.0	-
Date	22.05.2018 – 31.05.2018	31.05.2018 – 06.06.2018	06.06.2018 – 13.06.2018	13.06.2018 – 27.06.2018
Milestones	- beta release / - future freeze	- code freeze	- documentation completed / - final release / submission	- presentation prepared / - presentation
Time Budget	40	50	80	30
Tasks	- Implement remainging user stories / - Improve code base / - write integration tests	- Improve code base / - write integration tests / - write documentation	- fix eventual bugs / - write documentation / - submit documents
Documents / / Artefacts	- beta release bundle	- abstract / - management summary	- final release bundle / - poster / - personal reports / - time accounting	- presentation